## Slide 1: iClinicSys Status
Greg Ninobla/CHD ILOCOS
CP 1
Sept. 12, 2019

## Slide 2
CHD ILOCOS ICTU Strategic Function
Function | Indicator | Formula | Baseline | 2019 | 20 20 | 2021 | 2022
Measure and monitor progress then results of implementation of electronic medical record system (EMRs) in primary care and hospital facilities in the public sector | % of public health facilities in Region I implementing EMRs and submitting complete and timely information | No. of public health facilities with EMR submitting complete and timely information vs. number of all public health facilities | 15% 27 | 20% 36 | 50% 89 | 70% 125 | 100% 179
Notes: Layout 1

## Slide 3
Function | Indicator | Formula | Baseline | 2019 | 2020 | 2021 | 2022
Require ICT support for increased access, availability and equity of health services of health provider networks in UHC Implementation Sites (UHC-IS) | % of UHC-IS with list of health facilities that will serve as telehealth service hub for GIDA areas | No. of UHC IS with telehealth vs all UHC IS | 1 | 30% 1 | 50% 1 | 70% 1 | 100% 1
CHD ILOCOS ICTU Strategic Function
Notes: Layout 1

## Slide 4
UHC Implementing Sites for Luzon and NCR
Region | Region Name | Site | RHU | Public Hospitals | Total Public HF
1 | Ilocos | Dagupan (ICC) | 1 | 1 | 2
Notes: Layout 1

## Slide 5: Action/Implementation Plan
# | Activities | Time Frame | Performance Indicators | RESOURCE REQUIREMENT |  |  | Fund Source
 |  |  |  | Item | Details | Cost | 
1 | Conduct ICT Assessment of respective health facilities | October – December 2019 | Number of ICT Assessment conducted for health facilities | Per diems, Transportation | 6 IT Staff *1,500*3 days*179 facilities*3months 6 IT Staff *2,000*2 trips*179 facilities*3months | Per diem: 14,499,000.00 Transportation: 6,444,000.00 | SAA (KMITS)
2 | Submit consolidated ICT Assessment report to KMITS for budgeting and procurement of ICT resources | 1st quarter of year 2020 | Number of ICT Assessment report submitted to KMITS |  |  |  | 
3 | Conduct Decision Makers’ Orientation to respective UHC implementing sites | 1st quarter of year 2020 | Number of Decision Makers’ orientation conducted | Meals and snacks | 100(pax , facilitator, resource speaker)*350 | 35,000.00 | SAA (KMITS)
Notes: Know where we are going:
Framework for the work and financial planning:
Align the region’s work and financial plan with the national plan
Be strategic (How to go about converting inputs into outputs)
Determine how to convert resources, overcome constraints, using the identified inputs (resources) to reach the objectives or attain the desired outputs.
Inclusions, Strategy/Methods/Delivery Modes, Time Frame
    Training Plan
    System Monitoring Plan
    Risk Management Plan
    Workshop Plan
    Conference Plan
    Technical Assistance Plan
    Quality Assurance Plan
Identify and address resources and constraints
Set standards.
  Be consistent. Use verb or noun, e.g. “Monitor system” or “System Monitoring”
  Be clear with the activities, e.g. “Backup database” instead of “Backup”
  Group or categorize activities.
  Have standard tasks or steps for each activity.
Create measurable targets/milestones.
  Target is Quantity + Quality + Unit of Measure OR Service Outputs
  Be realistic with targets: Avoid under/over estimating. Use past data / accomplishment as basis.
When cascading work plan to individual staff: sum of individual targets must total with the section’s target.
Put timelines on everything.
  As much as possible, be specific with target dates.
Have basis or reference for computing budget.
  Details of the computed budget requirements must be available.

## Slide 6: Action/Implementation Plan
# | Activities | Time Frame | Performance Indicators | RESOURCE REQUIREMENT |  |  | Fund Source
 |  |  |  | Item | Details | Cost | 
4 | Conduct of Roll-out Training/Implementation | 2nd quarter of year 2020 | Number of roll-out trainings conducted | Board and Lodging | 100(pax , facilitator, resource speaker)*1,400*3 days*4 batches | 1,680,000.00 | SAA (KMITS)
5 | Technical Assistance | Q1 to Q4 | Number of health facilities provided with Technical Assisstance | Per diems, Transportation | 3 IT Staff *1,500*179 facilities*3 facilities(average)*12 months 3 IT Staff *2,000*2 trips*179 facilities*12 months | Per diem: 28,998,000.00 Transportation: 25,776,000.00 | SAA (KMITS)
6 | Monitoring and Evaluation | Q1 to Q4 | Number of health facilities monitored and evaluated | Per diems, Transportation | 3 IT Staff *1,500*179 facilities*3 facilities(average)*12 months 3 IT Staff *2,000*2 trips*179 facilities*12 months | Per diem: 28,998,000.00 Transportation: 25,776,000.00 | SAA (KMITS)
TOTAL |  |  |  |  |  | 132,206,000.00 | 
Notes: Know where we are going:
Framework for the work and financial planning:
Align the region’s work and financial plan with the national plan
Be strategic (How to go about converting inputs into outputs)
Determine how to convert resources, overcome constraints, using the identified inputs (resources) to reach the objectives or attain the desired outputs.
Inclusions, Strategy/Methods/Delivery Modes, Time Frame
    Training Plan
    System Monitoring Plan
    Risk Management Plan
    Workshop Plan
    Conference Plan
    Technical Assistance Plan
    Quality Assurance Plan
Identify and address resources and constraints
Set standards.
  Be consistent. Use verb or noun, e.g. “Monitor system” or “System Monitoring”
  Be clear with the activities, e.g. “Backup database” instead of “Backup”
  Group or categorize activities.
  Have standard tasks or steps for each activity.
Create measurable targets/milestones.
  Target is Quantity + Quality + Unit of Measure OR Service Outputs
  Be realistic with targets: Avoid under/over estimating. Use past data / accomplishment as basis.
When cascading work plan to individual staff: sum of individual targets must total with the section’s target.
Put timelines on everything.
  As much as possible, be specific with target dates.
Have basis or reference for computing budget.
  Details of the computed budget requirements must be available.

## Slide 7
Maraming salamat po!