## Implementation Plan
Learning & Development Activity Implementation Plan
Title of Program: Leadership and Self-Development Training |  |  | Date of Implementation: April 14-15, 2018
Program Designer/SME/TS: Poderoso B. Casuela Jr., MD, FPSP |  |  | Type of Activity: Training | No. of Attendees: 50
Program Admin: Jinalyn T. Noh, MD |  | Secretariat 1: Maricor Luna, RMT | [ ] In-House | [ /] External
|  | Secretariat 2: Alaine Kamille R. Lopez | Venue: Sun Rose Garden, Pulilan, Bulacan
Date | Activities | Person Responsible | Resources / Remarks | Budget
Pre-Conduct
2018-03-08 | LDI Proposal | Program Designer/SME/TS & Program Admin | Proposal signed by MCC as of March 21, 2018
Feb 4th week | Course Design Review | Program Designer/SME/TS | Program in Day 1 and 2
Feb 4th week | Book Venue & Caterer | Secretariat | Prep Specs & get 3 Quoatations
2018-03-07 | Finalization of Pax List | Program Admin | deadline March 6, 2018 (every dept)
2018-03-19 | Initiate Procurement Process | Program Admin
April first week | Prepare Materials (Using Checklist) | Program Admin & Secretariat | Two weeks before the activity
2018-04-12 | Send Reminders (at least 2 days before the activity) | Program Admin | Two days before the activity
March 3rd week | Check Venue | Program Admin | Sun Rose Garden
Within March | Team Briefing/Meeting 2 | Program Admin | Rizal Med & Training Provider
| Actual Conduct |  | April 14-15, 2018 | 150000
April first week | Team Briefing/Meeting 3 | Program Admin/Designer
| Check Facilitator/SME (Call/SMS) | Secretariat
| Venue Set-up | Program Admin & Secretariat
| Registration | Program Admin & Secretariat
| Opening Ceremonies | Program Admin
| Document Proceedings Level 1/2 Evaluation (Terminal Report) | Program Admin & Secretariat
| Coordination with Venue and Catering | Secretariat
| Print Documents | Program Admin
| Manage Learning Environment | Program Admin & Secretariat
| Closing Ceremonies | Program Admin
| Team De-Briefing/Meeting 4 | Program Admin
Post Conduct
| Secure Materials/Equipment | Secretariat
| Process Payments | Program Admin
| Tabulate and Summarize Evaluations | Program Admin
| Prepare Terminal/Training Report | Program Admin
| Turn-Over Program Documents to ISO/Records Custodian/Department Secretary | Secretariat
| Liquidation or Reimbursement | Program Admin
Prepared by: |  |  | Submitted to:
Signature/Date: |  |  | Signature/Date:
Program Administrator's Name: MARIEL T. RAMONEL |  |  | Name: MA. CHARISSA V. LEGASPI
Position/Title: Training Asssitant |  |  | Position/Title: Training Specialist IV
Note: The L&D Implementation Plan Form is to be accomplished by the Program Administrator in 4 copies (PA, PD, Secretariat and TO) for submission and consultation with the Training Specialist after the 1st team Briefing/Meeting. A final copy with the actual accomplishment dates is to be submitted to the Training Office 1 month after the last day of the activity.

## L&D Implemen Plan Checklist.
Learning & Development Activity Implementation Plan Checklist
Title of Program: Leadership and Self-Development Training |  |  | Date of Implementation: April 14-15, 2018
Program Designer/SME/TS: Poderoso B. Casuela Jr., MD, FPSP |  |  | Type of Activity: Training | No. of Attendees: 50
Program Admin: Jinalyn T. Noh, MD | Secretariat: Alaine Kamille R. Lopez/Marcicor B. Luna, RMT |  | [ /] Outside Rizal Med | [ ] In-House
Venue: Sun Rose Garden, Pulilan Bulacan
Date |  | Activities | Remarks/Specifications
Pre-Course Activities
February 3rd Week | Team Briefing/Meeting 1: Program Administrator & Designer meets the team (Faci, Secretariat) to discuss the Pre-course and Course Proper Activities, including assignment of tasks identification of timelines and addressing of inquiries and concerns |  | c/o Fil-Haribon Synergy Leadership Training Course
| LDI Proposal |  | Program Designer/SME/TS & Program Admin
2018-03-08 |  | Preparation of Proposal/Request Letter | PD/SME/TS
2018-02-28 |  | Request for Pax Letter | PD/SME/TS
2018-03-08 |  | Accomplishment of Proposal Template
2018-03-08 |  | HPO Draft (recommended)
|  | Estimated Budget | 150000
Quotations from 3 Providers if needed (i.e. Food, Venue, SME)
| Course Design Review |  | Program Designer/SME/TS
February 3rd Week |  | Training Plan | c/o Fil-Haribon Synergy Leadership Training Course
March first week |  | Workshop Slides | c/o Fil-Haribon Synergy Leadership Training Course
April first week |  | Manuals & Handouts | handouts only for the activities / one week before
|  | Others.. | Physical Activities
| Book Venue & Caterer |  | Secretariat
Booking of Venue
In-House: accomplish Use of Venue form (Auditorium, Pantry, Conference Room, others)
Others (Outside Rizal Med):__________________
Sun Rose Garden, Pulilan Bulacan
|  | Meet-up with Caterer for Menu & Other Requirements | (food - provided by the venue)
|  | Equipment request/reservation (i.e. IT/Engineering) | provided by the venue
2018-03-08 | Finalizations of Pax List |  | Program Admin & Secretariat
2018-03-08 |  | HPO of Pax including Amendments/Addendum | HPO only
2018-03-26 |  | Dissemination of HPO | Sec | March 4th week
2018-03-28 |  | Confirmation of Attendance with the Participant and Immediate Supervisor | Sec | target date for confirmation of attendance
|  | Printing of Attendance Sheet | one week before
|  | Certificate Draft (Soft Copy) | one week before
2018-03-19 | Initiate Procurement Process |  | Program Admin
|  | Cash Advance Voucher | already in the Procurement
|  | HPO for Authority to CA | for signing/approval of MCCII
Attach Signed HPO of Pax
|  | PR/RIS | done as of awaiting HPO for Authority to Cash Advance
Other Vouchers for External Providers (i.e. Venue/Catering/Manual & Materials Repro)
| Prepare Materials Using Checklist (1 - 2 weeks prior to the activity) |  | Program Admin & Secretariat
Prepare the required LDI Checklist ( at least 2 wks. before)
Prepare required IARs ( at least 2 wks. before)
|  | Pack Training Kits/TS (at least 1 week before) | Sec
|  | Print Handouts (at least 1 week before) | Sec
|  | Prepare Manuals / Slides (at least 2 wks. before) | Sec
|  | Shop for Supplies and Materials (at least 1 wk. before) | Sec
| Send Reminders (at least 2 days before the activity) |  | Program Admin
Facilitators/SME/Resource Speakers (secure slides soft and/or hard copy)
Participants (Call/Text Blast)
| Check Venue (at least 1 day before the activity) |  | Program Admin
Caterer (Water Dispenser)
Venue Set-up (coordinate with Secretariat/ M8/Engineering)
Equipment (Camera, LCD, Laptop/s, Mic, Clicker)
Team Briefing/Meeting 2: Program Administrator meets or simply coordinates with the team (Designer, Secretariat) to check on the accomplished tasks and review the Course Proper Activities
Course Proper Activities
Team Briefing/Meeting 3: Program Administrator meets the team briefly (Faci, Secretariat) 1 hour before the program begins to review task/role assignments during Course Proper and address inquiries and concerns
| Check Facilitator/SME (Call/SMS) |  | Program Admin
| Venue Set-Up (if possible day before the activity) |  | Program Admin & Secretariat
Oversee Set-up and Prep Easel Sheets needed
|  | Prep of Registration/Pax/Food Tables | Sec
|  | Venue Set-up (tables/chairs/Easel Stand/Laptops/LCD/Clicker/Mic) | Sec
Prep of Slides for projection and Terminal Report Template on the designated laptops
| Registration |  | Program Admin & Secretariat
Greet participants
|  | Issue name tags/kits | Sec
|  | Check attendance (text/call) missing pax/Faci/SME | Sec
| Opening Ceremonies |  | Program Admin
Opening Prayer
Flag Ceremony
Course/Workshop Norms (except for CSCW)
Pre-Test (if any)
Introduce SME/Facilitator (Optional)
| Document Proceedings and Highlights (Terminal Report) hard & soft copies |  | Program Admin & Secretariat
Securing Photos/Videos (Output, Pax during activities)
Encoding highlights and POA
Building on the Terminal Report
|  | Arrange Class and Before & After Picture Taking | Sec
Before & After Slide Show
Coordination with Venue and Catering
|  | Complete & Timely Delivery/Serving of Food | Sec
| Manage Learning Environment |  | Program Admin & Secretariat
Conduct Ice Breaker/Energizer/Learning Review
Link Modules (if with various Facilitators/SMEs)
|  | Monitor attendance (text/call missing pax if needed) | Sec
|  | Ensure participants log in/out of the attendance sheet | Sec
Respond to Facilitator/Participant inquiries/Requests (i.e. food requirements
| Closing Ceremonies |  | Program Admin & Secretariat
Discuss Post-Course Activities/Assignments (if any)
Post Test (if any)
Level 1 Evaluation - Post Training Evaluation (PTE)
|  | Collect ID Tags and other output (if needed) | Sec
Discuss Level 2 Evaluation - Training Workshop Report (TWR)
Team De-Briefing/Meeting: Program Administrator meets the team briefly (Faci, Secretariat) after the program (last day or unpacking day) to review Course Proper Performance, discuss Post-Course Activities, take note of strengths and areas for improvement , and address issues and concerns (if needed, to be relayed to the Rizal Med Training Specialist).
Post-Course Activities
| Secure Materials/Equipment |  | Secretariat
Gather and safekeep workshop outputs, attendance and letters
Gather and unpack Kits/Materials/Supplies
Return Borrowed Equipment (Camera/LCD/Laptop/Clicker)
| Print Documents |  | Program Admin
Certificate of Completion
Certificate of Appearance
Class Picture (Optional)
TWR Memo (1 week after the activity)
|  | Distribution of Memo | Secretariat
| Process Payments Designer/TS |  | Program Admin
Ensure payment and safe keep receipts of expenses incurred
| Tabulate and Summarize Evaluations |  | Program Admin
Pre-Test (if any)
Post-Test (if any)
Level 1 Evaluation - PTE Summary Report
| Prepare Training Report |  | Program Admin
Terminal/Training Report - Level1/2 Evaluation
| Turn-Over Program Documents to ISO/Records Custodian/Department Secretary |  | Secretariat
Final Directory and/or Attendance Sheet of Participants
Updated Profile of SME
Soft Copy of Learning Materials
Soft Copy of Photos and Videos
Turnover of sorted Copies Photos & Commitment Video (for CSCW) to CC-IHOMS Video Presentation creation)
| Liquidation or Reimbursement |  | Program Admin
Liquidation/Reimbursement Report
Liquidation/Reimbursement Report
Attach PR/RIS/IAR
Attach Attendance Sheet & Cert of Appearance
Excuse/Explanation Letters for Absences
Prepare Report of Cash Disbursement (RCD)
Prepared by: |  |  | Approved by:
Signature/Date: |  |  | Signature/Date:
Program Admin's Name: |  |  | Program Designer's Name:
Position/Title: |  |  | Position/Title:
Checked by: |  |  | Checked by:
Signature/Date: |  |  | Signature/Date:
Name: |  |  | Name:
Position/Title: |  |  | Position/Title:
Program Administrator
Secretariat
Program Designer/SME/TS
Note: The L&D Implementation Plan Checklist is to be accomplished and used by the Program Administrator during the Pre, Course and Post Conduct phase, to ensure the smooth and successful delivery of the activity. A photocopy of the finalized checklist is to be submitted to the Training Office, together with the L&D Implementation Plan Form within 1 month after the last date of the activity.

## PREP_Materials Checklist
L&D Activity Materials & Supplies Checklist
Prep Date: March 5, 2018 |  | Activity Date/s: April 14-15, 2018
Activity Title: Leadership and Self-Development Training |  | Type of Activity: Training
Program Administrator: Jinalyn T. Noh, MD |  | Venue: Sun Rose Garden, Pulilan Bulacan
Secretariat: Lynette Marie C. Ocampo/Maricor B. Luna/Alaine Kamille R. Lopez |  | No. of Attendees: 50
Budget/Speakers/Venue/Others | Details | Confirmed/ Requested | Remarks
Cash Advance / Other fund source | 8000 |  | for sigining of MCCII
HPO of CA and Participants |  |  | for sigining of MCCII (CA & Participants)
Training Venue Reservation Form/Contract
Food Provider / Caterer |  |  | provided by the venue
Resource Speaker/s | 3
Spiel for the Introduction of Speaker/s | 1 |  | Dr. Poderoso B. Casuela
Facilitator/s | 11
Others:
Paper & Electronic Files (as needed) | Quantity | Available | To Buy | Remarks
Manuals/Hand-Outs |  |  |  | c/o Fil-Haribon Synergy
Hard/Soft Copy of Slides & Agenda (for speakers) |  |  |  | c/o Fil-Haribon Synergy
Attendance Sheet w/ clipboard | 2
Certificates (soft copy - draft for editing) | 40
Manila Paper | 10
Others:
Evaluation / Rating Forms
Pre-Test
Post-Test
PTE - Post Training Evaluation | class size + 5
TWR - Training/Workshop Report | class size + 5
Others:
Materials (as needed)
Manila Paper | 10
Paper for Certificates | 40
ID Jackets for Name Tags | 40
Others:
Others:
Equipment & Peripherals (as needed)
Boxes and/or Luggage |  |  |  | provided by the venue
Easel Stand/White board
Stopwatch / Timer
Speakers with cables / PA System
Microphone
Micro SDs or USB - Lively & instrumental music
Presentation Laptop
Report Laptop
Clicker/ Presenter with extra batteries
LCD projector
Extension Cord/s
Camera
Others:
PRIZES (Optional for early birds and activities)
Candies/Chocolates |  |  |  | c/o by the Fil-Haribon Synergy
Small Tokens |  |  |  | c/o by the Fil-Haribon Synergy
Others:
Food/Supplies (as needed) | Quantity | Available | To Buy | Remarks
Snacks |  |  |  | Provided by the Venue
Lunch
Candies/Nibbles
Water Dispenser
Water Gallons/ Bottled Water
Drinks
Tissue Roll
Tissue Square
Plastic Cups
Paper Cups
Instant Coffee
Stirrers
Candies/Nibbles
Others:
Prepared by:
_____________________________ ___________________________ |  | _____________
Program Admin's Name & Signature Secretariat's Name & Signature
Checked by:
_____________________________
Printed Name & Signature
Note: The L&D Activity Materials & Supplies Checklist is to be accomplised by the Program Administrator and handed over to the Secretariat as a packing and unpacking guide for the activity.