**2016 Action Plan for Negros Island Region in the Generation of Health Statistics for the Negros Island Region**

Knowledge Management and Information Technology Service

|  |  |  |  |
| --- | --- | --- | --- |
| **Activity** | **Performance Indicator** | **Target Date** | **Responsible Division** |
| Update of Philippine Standard Geographic Code (PSGC) in the National Health Data Dictionary | No. of database updated | Feb | KMD |
| Update of Libraries/Reference for PSGC in each DOH Info System, websites/pages | No. of DOH information systems, websites/pages updated | March | SSED -System Development and System Configuration Management Section and  KMD Website Team |
| Provision of orientation/training of trainers for Program Managers of Negros Island Region | No. of trainings conducted | June | SSED & KMD |
| Update or revise Health Maps (www.map.doh.gov.ph)  and National Health Facility Registry (NHFR) (www.nhfr.gov.ph) | No. of systems updated | June | KMD |
| Segregate Provincial Profiles for two provinces | No. of provincial profiles segregated | April | KMS |
| Produce available current statistics from various systems such as National Health Facility Registry (NHFR), Health Atlas, Provincial Profile, Registries, etc | No of statistics produce | When approved/ requested/needed | KMD & SSED |

Submitted:

**CRISPINITA A. VALDEZ, CESO III**

Director IV